## Annual programme
BUILDING | [5 empty] | BUILDING MANAGER
Delivered to the co-owners' representative: |  |  |  | Expected reserve fund for the year (EUR): |  |  | Co-owners' representative:
ANNUAL MAINTENANCE PROGRAMME | [8 empty] | year | 2027
No. | Item | Part of building | Source (work order, request, finding) | Maintenance type | Priority | Cost estimate (EUR) | Deadline | Carried out by | Status | Note
| Example: replace a worn valve | Boiler room | Work order 2026-114, temporary part | Necessary repair | High | 650 | March | Outside servicer | Planned | Amount from the contractor quote
| Annual service of burner and pumps | Boiler room | Service report, recurring | Regular | High |  | Before the heating season |  | Planned
| Clean and repair gutters | Roof | Work orders after rain | Regular | Medium |  | October |  | Planned
| Adjust and service the entrance door | Entrance | Co-owner work requests | Regular | Medium |  | April |  | Planned
| Lift inspection and service | Lift | Contract with an authorised servicer | Regular | High |  | Per contract |  | Planned
| Fire safety equipment inspection | Common areas | Service report | Regular | High |  | Per contract |  | Planned
| Repaint the stairwell | Stairwell | Inspection finding | Capital | Low |  | Summer |  | Planned
Total cost estimate (EUR):
Expected reserve fund (EUR):
Difference, reserve fund minus estimate (EUR):
Estimate by priority |  |  |  | Estimate by maintenance type
High |  |  |  | Regular
Medium |  |  |  | Urgent repair
Low |  |  |  | Necessary repair
Capital
Modern & Simple Work Order and Maintenance Management CMMS
Note on G11: Example row: the amount is an illustration, enter the amount from the contractor quote or contract.

## Multi-year programme
MULTI-YEAR MAINTENANCE PROGRAMME
Enter each amount under the year you plan the work. The years follow the programme year on the "Annual programme" sheet.
Item | Part of building | Maintenance type | Priority | Cost estimate (EUR) |  |  |  | Allocated (EUR)
Example: roof renovation | Roof | Capital | Medium | 24000 | 12000 | 12000
Total per year (EUR):
Modern & Simple Work Order and Maintenance Management CMMS
Note on E6: Example row: the amount is an illustration, enter the amount from the contractor quote or contract.

## Instructions
Instructions for the annual maintenance programme
Field | Instruction
BUILDING | Enter the building address and, if there is one, its register reference.
BUILDING MANAGER | Enter the building manager and the contact person.
year | Enter the year the programme is proposed for (orange field next to the title).
Delivered to the co-owners' representative | Date of the written delivery of the proposal (format: DD.MM.YYYY.).
Co-owners' representative | Name of the representative the proposal goes to.
Expected reserve fund | Shared reserve fund expected for the programme year.
Item and part of building | One row per job. The first row is an example: overwrite or delete it.
Source | Number of the work order, work request or inspection finding from last year.
Maintenance type | Regular, urgent repair, necessary repair or capital (drop-down list).
Priority | High, medium or low: safety and basic living conditions first, then whatever repeats.
Cost estimate | Amount from the contractor quote or contract, not a guess.
Deadline, carried out by, status | Planned month, contractor and progress during the year.
Multi-year programme | Items which do not fit the reserve fund, spread across years.
Formulas
No. | Item number, filled in automatically once an item is entered.
Total cost estimate | Sum of the cost estimate column.
Difference | Expected reserve fund minus the total estimate. A negative amount means the programme exceeds the reserve fund.
Estimate by priority and type | Sum of the estimates for each priority and each maintenance type.
Multi-year programme years | The five years after the programme year.
Building manager deadlines (Croatian Act on the Management and Maintenance of Buildings, NN 152/24, Article 52)
Deadline | Manager's obligation
15 November | Proposed annual maintenance programme to the co-owners' representative.
31 December | Proposed multi-year maintenance programme.
by February | Annual management report for the previous year.
30 days after a job | Notice to co-owners about completed works.
3 hours after a report | Arrange the urgent repair, unless outside circumstances prevent it.
If the co-owners adopt no annual or multi-year programme, they pay the reserve fund at five times the last adopted amount (Article 29). The template does not replace the co-owners' decision or the management contract.
getserwizz.com